## Daily Production Report
Daily Production Report
PROD. NUMBER |  |  |  | PRODUCTION TITLE | [11 empty] | START DATE | [7 empty] | END DATE
Daily Production Details
| Director | [15 empty] | Date
| Producer | [15 empty] | Day # | [11 empty] | of
| 1st AD | [15 empty] | Crew Call
| 2nd AD | [15 empty] | Shooting Call
| Set(s) | [15 empty] | 1st Shot
1st Meal Start
1st Meal End
| Location(s) | [15 empty] | 1st Shot After Meal
2nd Meal Start
2nd Meal End
Camera Wrap
Company Wrap
Media Cards
| CAMERA CARD # |  | CAPACITY |  | STARTING % |  |  | ENDING % |  |  | USED TODAY | [5 empty] | ID NUMBERS OF SOUND CARD(S) USED
Progress Tracker
| DAILY PROGRESS |  |  | SCENES |  | PAGES |  |  | MINUTES |  |  | SETUPS |  |  |  |  | TOTAL DATA ALLOCATION
| In Script | [24 empty] | Gb
Added Today
| Deleted Today | [15 empty] | TOTAL SHOT |  |  |  | PAGES % |  |  |  | DATA Gb |  |  |  |  | DATA %
| New Total |  |  | 0 |  | 0 |  |  | 0:00 |  |  | 0 |  |  |  |  | Previous | [5 empty] | % |  |  |  |  | Gb |  |  |  | %
| Shot Previous | [15 empty] | Today | [5 empty] | % |  | 0 |  |  | Gb |  |  |  | %
| Planned Today | [15 empty] | To Date | [5 empty] | % |  | 0 |  |  | Gb |  |  |  | %
| Actual Today | [15 empty] | Remaining | [5 empty] | % |  |  |  |  | Gb |  |  |  | %
| Shot to Date |  |  | 0 |  | 0 |  |  | 0:00 |  |  | 0
| Remaining |  |  | 0 |  | 0 |  |  | 0:00 |  |  | 0
EQUIPMENT MALFUNCTION • PROBLEMS • PRODUCTION DELAYS
Date: |  |  |  | Call Time: | [17 empty] | Daily Production Report
CAST | [5 empty] | CHARACTER | [6 empty] | MINOR |  | S/W/F |  |  | REPORT |  | REPORT |  |  | DISMISS |  |  |  | DISMISS |  |  |  | MEAL
[18 empty] | MAKEUP |  | ON SET |  |  | ON SET |  |  |  | MAKEUP |  |  |  | TIME(S)
EXTRAS | [17 empty] | REPORT |  |  |  |  | DISMISS | [7 empty] | MEAL(S)
PRODUCTION |  | NAME |  |  |  |  | TIME IN |  |  | TIME OUT |  |  |  | EDITORIAL |  |  |  |  | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT
Director | [13 empty] | Editor
Producer | [13 empty] | Asst. Editor
UPM | [13 empty] | CATERING |  |  |  |  | NAME | [11 empty] | REPORT
1st AD | [13 empty] | Breakfast
2nd AD | [13 empty] | Lunch
Script Supe | [13 empty] | 2nd Meal
Video Assist | [13 empty] | TRUCKS |  |  |  |  | DRIVER / PASSENGER NAMES | [11 empty] | VEHICLE #
CAMERA |  | NAME |  |  |  |  | TIME IN |  |  | TIME OUT |  |  |  | Grip/Electric
DP | [13 empty] | Generator
Camera Op | [13 empty] | ADDITIONAL |  |  |  |  | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT
1st AC
2nd AC
GRIP |  | NAME |  |  |  |  | TIME IN |  |  | TIME OUT
Key Grip
Best Grip
Dolly Grip
ELECTRIC |  | NAME |  |  |  |  | TIME IN |  |  | TIME OUT
Gaffer
Best Electric
3rd Electric
SOUND |  | NAME |  |  |  |  | TIME IN |  |  | TIME OUT
Sound Mixer
Boom Op
ART |  | NAME |  |  |  |  | TIME IN |  |  | TIME OUT
Prod. Designer
Art Director
Art Assist
CREW DELAYS / EXCUSES / MEDICAL / HEALTH EXPLANATIONS (include additional documentation as needed)

## SAMPLE
Daily Production Report
PROD. NUMBER |  |  |  |  | PRODUCTION TITLE | [16 empty] | START DATE | [7 empty] | END DATE
23bth |  |  |  |  | Production Management: The Movie | [16 empty] | 2022-10-24 | [7 empty] | 2022-10-29
Daily Production Details
| Director |  |  |  | Allison Parker | [17 empty] | Date | [6 empty] | 2022-10-25
| Producer |  |  |  | John Adams | [17 empty] | Day # | [6 empty] | 2 |  |  |  |  | of | 6
| 1st AD |  |  |  | Sam Hernandez | [17 empty] | Crew Call | [6 empty] | 6:00
| 2nd AD |  |  |  | Spencer Curtis | [17 empty] | Shooting Call | [6 empty] | 7:30
| Set(s) |  |  |  | INT. BOB'S HOUSE (BASEMENT, KITCHEN) | [17 empty] | 1st Shot | [6 empty] | 7:55
[5 empty] | EXT. BOB'S HOUSE | [17 empty] | 1st Meal Start | [6 empty] | 12:08
[5 empty] | EXT. PARK | [17 empty] | 1st Meal End | [6 empty] | 12:55
| Location(s) |  |  |  | (1) 1230 Monroe St, Tallahassee, FL | [17 empty] | 1st Shot After Meal | [6 empty] | 13:26
[5 empty] | (2) Dorothy Oven Park, 4837 Thomasville Rd, | [17 empty] | 2nd Meal Start | [6 empty] | –
[5 empty] | Talllahassee, FL | [17 empty] | 2nd Meal End | [6 empty] | –
[23 empty] | Camera Wrap | [6 empty] | 18:10
[23 empty] | Company Wrap | [6 empty] | 18:55
Media Cards
| CAMERA CARD # |  |  | CAPACITY |  |  | STARTING % |  |  |  |  | ENDING % |  |  |  | USED TODAY | [6 empty] | ID NUMBERS OF SOUND CARD(S) USED
| SSD 56 |  |  | 512 |  | Gb | 100 |  |  | % |  | 75 |  | % |  | 128 |  |  |  | Gb |  |  | 114
118
Progress Tracker
| DAILY PROGRESS |  |  |  | SCENES |  |  | PAGES |  |  |  |  | MINUTES |  |  |  | SETUPS | [5 empty] | TOTAL DATA ALLOCATION
| In Script |  |  |  | 28 |  |  | 11.75 |  |  |  |  | 12:00 |  |  |  | 91 | [5 empty] | 780 | [8 empty] | Gb
| Added Today |  |  |  | 0 |  |  | 0 |  |  |  |  | 0:00 |  |  |  | 3
| Deleted Today |  |  |  | 0 |  |  | 0 |  |  |  |  | 0:00 |  |  |  | 1 | [5 empty] | TOTAL SHOT |  |  |  | PAGES % |  |  |  | DATA Gb |  |  |  |  | DATA %
| New Total |  |  |  | 28 |  |  | 11.75 |  |  |  |  | 12:00 |  |  |  | 93 | [5 empty] | Previous |  |  |  | 21 |  | % |  | 132.68 |  |  | Gb |  | 17.0103 |  | %
| Shot Previous |  |  |  | 2 |  |  | 1.5 |  |  |  |  | 1:30 |  |  |  | 23 | [5 empty] | Today |  |  |  | 24.4681 |  | % |  | 128 |  |  | Gb |  | 16.4103 |  | %
| Planned Today |  |  |  | 4 |  |  | 2.875 |  |  |  |  | 2:53 |  |  |  | 25 | [5 empty] | To Date |  |  |  | 37.234 |  | % |  | 260.68 |  |  | Gb |  | 33.4205 |  | %
| Actual Today |  |  |  | 4 |  |  | 2.875 |  |  |  |  | 2:53 |  |  |  | 27 | [5 empty] | Remaining |  |  |  | 62.766 |  | % |  | 519.32 |  |  | Gb |  | 66.5795 |  | %
| Shot to Date |  |  |  | 6 |  |  | 4.375 |  |  |  |  | 4:23 |  |  |  | 50
| Remaining |  |  |  | 22 |  |  | 7.375 |  |  |  |  | 7:37 |  |  |  | 43
EQUIPMENT MALFUNCTION • PROBLEMS • PRODUCTION DELAYS
Bulb blew on a junior.
Camera Battery malfunctioned and was switched out by ER staff.
Thunderstorms in afternoon caused 50-minute delay.
Used 8 minutes of grace before 1st meal.
Date: |  | 2022-10-25 |  |  | Call Time: |  |  |  | 6:00 | [15 empty] | 23bth |  |  | Daily Production Report
CAST | [7 empty] | CHARACTER | [9 empty] | MINOR |  |  | S/W/F |  |  | REPORT |  | REPORT |  |  | DISMISS |  |  |  | DISMISS |  |  |  | MEAL
[24 empty] | MAKEUP |  | ON SET |  |  | ON SET |  |  |  | MAKEUP |  |  |  | TIME(S)
Tom Archer | [7 empty] | Bob | [12 empty] | W |  |  | 7:00 |  | 7:15 |  |  | 18:10 |  |  |  | 18:30 |  |  |  | 12:08
Susan McMahon | [7 empty] | Sarah | [12 empty] | W |  |  | 7:05 |  | 7:15 |  |  | 18:10 |  |  |  | 18:30 |  |  |  | 12:08
Ryan Rogers | [7 empty] | Akil | [12 empty] | SW |  |  | 7:00 |  | 7:15 |  |  | 18:10 |  |  |  | 18:30 |  |  |  | 12:08
Chuck Martin | [7 empty] | Joe | [12 empty] | SWF |  |  | 14:00 |  | 14:30 |  |  | 18:10 |  |  |  | 18:30 |  |  |  | –
Armando Rodriguez | [7 empty] | Pedro | [9 empty] | X |  |  | SWF |  |  | 14:00 |  | 2:30PM |  |  | 18:10 |  |  |  | 18:30 |  |  |  | –
EXTRAS | [23 empty] | REPORT |  |  |  |  | DISMISS | [7 empty] | MEAL(S)
20 park extras | [23 empty] | 14:30 |  |  |  |  | 17:15 | [7 empty] | –
PRODUCTION |  |  | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT |  |  |  | EDITORIAL | [5 empty] | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT
Director |  |  | Allison Parker | [7 empty] | 5:35 |  |  |  | 18:55 |  |  |  | Editor | [5 empty] | Andrew Meyers | [7 empty] | – |  |  |  | –
Producer |  |  | John Adams | [7 empty] | 5:30 |  |  |  | 18:55 |  |  |  | Asst. Editor | [5 empty] | Morgan Hall | [7 empty] | 18:21 |  |  |  | 18:55
UPM | [18 empty] | CATERING | [5 empty] | NAME | [11 empty] | REPORT
1st AD |  |  | Sam Hernandez | [7 empty] | 5:30 |  |  |  | 18:55 |  |  |  | Breakfast | [5 empty] | Craft Service | [11 empty] | 6:00
2nd AD |  |  | Spencer Curtis | [7 empty] | 5:30 |  |  |  | 18:55 |  |  |  | Lunch | [5 empty] | Olive Garden | [11 empty] | 12:00
Script Supe |  |  | Hillary Wallace | [7 empty] | 5:47 |  |  |  | 18:55 |  |  |  | 2nd Meal
Video Assist | [18 empty] | TRUCKS | [5 empty] | DRIVER / PASSENGER NAMES | [11 empty] | VEHICLE #
CAMERA |  |  | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT |  |  |  | Grip/Electric | [5 empty] | Ben Epstein / Joanna Truman | [11 empty] | 7
DP |  |  | Nik Huyhn | [7 empty] | 5:42 |  |  |  | 18:55 |  |  |  | Generator
Camera Op | [18 empty] | ADDITIONAL | [5 empty] | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT
1st AC |  |  | Najaa Young | [7 empty] | 5:47 |  |  |  | 18:55 |  |  |  | PA | [5 empty] | Mike Gioulakis | [7 empty] | 6:00 |  |  |  | 18:55
2nd AC |  |  | Fran Ervin | [7 empty] | 5:43 |  |  |  | 18:55 |  |  |  | PA | [5 empty] | John Shadigg | [7 empty] | 6:00 |  |  |  | 18:55
GRIP |  |  | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT
Key Grip |  |  | Ben Epstein | [7 empty] | 5:50 |  |  |  | 18:55
Best Grip |  |  | Joanna Truman | [7 empty] | 5:50 |  |  |  | 18:55
Dolly Grip
ELECTRIC |  |  | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT
Gaffer |  |  | Akil Franklin | [7 empty] | 5:51 |  |  |  | 18:55
Best Electric
3rd Electric
SOUND |  |  | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT
Sound Mixer |  |  | Ryland Jones | [7 empty] | 6:03 |  |  |  | 18:55
Boom Op
ART |  |  | NAME | [7 empty] | TIME IN |  |  |  | TIME OUT
Prod. Designer |  |  | Ariya Watty | [7 empty] | 5:20 |  |  |  | 18:55
Art Director |  |  | Alex Smith | [7 empty] | 5:20 |  |  |  | 18:55
Art Assist
CREW DELAYS / EXCUSES / MEDICAL / HEALTH EXPLANATIONS (include additional documentation as needed)
Sound Mixer was 3 minutes late due to an accident on Monroe St.
Key Grip was stung by a bee and treated with bug sting spray.
DP slipped on a wet ramp and skinned their knee; cleaned with alcohol wipe and bandaged.