## PR Front
Daily Production Report
FSU College of Motion Picture Arts
A5100 University Center
Tallahassee, FL 32306
OFFICE: (850) 645-8675
Producer: _ | [25 empty] | [DATE]
Director: _ | [25 empty] | Day: _ of _
STATUS OF SHOOTING
|  |  |  | 1ST UNIT |  | 2ND UNIT |  | PREP | REHEARSAL |  | HOLIDAYS | TRAVEL | IDLE |  | TOTAL | X | ON SCHEDULE |  |  |  |  | DATE STARTED:
# OF ACTUAL DAYS | [15 empty] | - | AHEAD |  | - | DAYS |  | SCHEDULED FINISH:
REVISED FINISH:
# OF SCHEDULED DAYS | [15 empty] | - | BEHIND |  | - | DAYS |  | CURRENT SCRIPT:
CURRENT SCHEDULE:
SCENES |  |  | SET DESCRIPTION | [13 empty] | PGS |  |  | LOCATION
CREW CALL
SHOOTING CALL
FIRST SHOT
MEAL OUT
MEAL IN
FIRST SHOT AFTER
CAMERA WRAP
LAST MAN OUT
GRACE (Y/N)
EXTENSION (Y/N)
COMPANY WRAP
[15 empty] | Total: |  | 0
SCRIPT NOTES
[5 empty] | PAGES |  |  | SCENES |  |  |  | TIME |  | SET-UPS | [7 empty] | SCENE BREAKDOWN
ORIGINAL SCRIPT | [9 empty] | PREVIOUS |  | 0:00 |  | 0 |  | COMPLETED
REVISIONS ADDED | [15 empty] | PARTIALLY SHOT
REVISIONS DELETED | [9 empty] | TODAY | [5 empty] | SCHEDULED & NOT SHOT
CURRENT SCRIPT |  |  |  |  | 0 |  |  | 0 | [7 empty] | NOT SCHEDULED & SHOT
SHOT PREVIOUS | [9 empty] | TOTAL |  | 0:00 |  | 0 |  | WILDLINES
SHOT TODAY | [15 empty] | RESHOT
TOTAL TO DATE |  |  |  |  | 0 |  |  | 0 |  | SCRIPT NOTES
TO BE SHOT
ROLLS |  |  |  |  | SOUND |  |  |  |  | ROLLS |  | A | B
PREVIOUS | [9 empty] | PREVIOUS
TODAY | [9 empty] | TODAY
TO DATE | [9 empty] | TO DATE
EXHIBIT G
EXHIBIT G | [10 empty] | STATUS | RPT TO BASE | RPT ON SET |  | OUT FROM SET | OUT FROM BASE |  |  |  | MEAL OUT | MEAL IN | LV REST AREA | ARRV TO BASE |  | LV FROM BASE | ARRV REST AREA | MPV | STUNT ADJ | ADD'L NOTES
# | ACTOR | [5 empty] | ROLE
NOTES:
STATUS KEY: |  | S: Start TR: Travel W: Work H: Hold F: Finish FT: Fitting R: Rehearsal T: Test D: Drop P: Pickup | [15 empty] | NOTES KEY: |  | SA: Stunt Adjustment FC: Forced Call NDB: Non-Deductible Breakfast NP: Not Photographed K: Minor G: Grace
BACKGROUND PERFORMERS
NON-UNION
# |  | RATE |  | IN |  | MEAL |  |  | WRAP |  | NDB | MPV | ADJUSTMENTS
4 |  | -
NOTES | [25 empty] | Stand-Ins |  |  | 0
[26 empty] | Photo Double | Photo Double |  | -
[26 empty] | Non-Union BG | Non-Union BG |  | -
[26 empty] | TOTAL BG | TOTAL BG
SAG Mileage RT: 0 ADJUSTMENTS KEY: A: Auto C: Costume H: Hair MU: Make-Up S: Smoke W: Wet OCD: Off-Camera Dialogue P: Prop K: Minor
Unit Production Manager: | [23 empty] | 1st Assistant Director:
2nd Assistant Director:

## PR Back
| CREW CALL: | 0:00 | [15 empty] | [DATE]
| GRACE (YES/NO): | 0 | [15 empty] | Day: _ of _
# |  |  | IN | LUNCH IN | LUNCH OUT | OUT | NDB | MPV | # |  |  | IN | LUNCH IN | LUNCH OUT | OUT | NDB | MPV | # |  | IN | LUNCH IN | LUNCH OUT | OUT | NDB | MPV
PRODUCTION | [8 empty] | ART DEPARTMENT | [8 empty] | PRODUCTION OFFICE
1 | Producer | [7 empty] | 1 | Production Designer | [7 empty] | 1 | Production Coordinator
1 | Director
1 | UPM
1 | 1st AD | [7 empty] | 1 | Art Dept Assistant
1 | 2nd AD
1 | AD PA
COSTUMES
[9 empty] | 1 | Set Costumer
EPK
[18 empty] | 1 | EPK
SCRIPT SUPERVISOR
1 | Script Supervisor | [7 empty] | 1 | Extras Trailer Costumer
CAMERA | [8 empty] | 1 | Costumer
1 | Director of Photography | [7 empty] | 1 | Costumer | [7 empty] | 1 | 1.25
1 | Camera Operator | [7 empty] | 1 | Stitcher | [7 empty] | VFX
1 | 1st AC
1 | 2nd AC
SET DECORATION
[9 empty] | 1 | Production Designer
EDITORIAL
[18 empty] | 1 | Editor
[18 empty] | 1 | Assistant Editor
SOUND & VIDEO
1 | Sound Mixer
1 | Boom Operator
CASTING
| Sound Utility (Cast) | [16 empty] | 1 | Casting Director
CONSTRUCTION
[18 empty] | 1 | Extras Casting Dir
SET LIGHTING
1 | Gaffer
TRANSPORTATION
1 | BB Electric
CRAFT SERVICE
OTHER CREW
| Add'l Set Lighting Technician | [7 empty] | 1 | Assist Craft Service
1 | Add'l Set Lighting Technician | [7 empty] | TECH ADVIDORS
1 | Add'l Set Lighting Technician
CATERING
GRIP
1 | Key Grip
1 | BB Grip
1 | Grip
Crew Lunches ready @
[11 empty] | Extras Lunches ready @ | NA
Total Lunches ordered
Total Lunches served
PROPS
1 | Prop Master
[9 empty] | 1 | Covid PA
LOCATIONS
1 | Location Mgr | [7 empty] | SET MEDICS | [8 empty] | PICTURE CARS
1 | Location Assistant | [16 empty] | 1 | Bosch Jeep
[18 empty] | 1 | Black SUV
[18 empty] | 1 | Money Chandler's Car
[9 empty] | 1 | Prepping Medic
SPFX
1 | SPFX
1 | SPFX
PRODUCTION NOTES:
1 | SAFETY MEETING:
2 | MEALS:
3 | SAG MILEAGE:
4 | RE-RATES:
5 | LOSS / DAMAGE:
6 | INJURY/MEDICAL:
7 | EQUIPMENT:
8 | DGA: | MEAL ALLOWANCE:
WRAP ALLOWANCE:
EXTENDED DAY:
9 | Note | The company shot Epsiode 4 from crew call to 8:23A and from 9:50A to wrap; Epsiode 2 from 823A to 950A .
The Company moved from location 1 (Red Studios) to location 2 (800 S Plymouth Blvd, 90005) at 437P.

## SAMPLE-PR Front
Daily Production Report
FSU College of Motion Picture Arts
A5100 University Center
Tallahassee, FL 32306
OFFICE: (850) 645-8675
Producer: Lisette Delgado | [25 empty] | 2024-10-10
Director: Raven Carter | [25 empty] | Day: 1 of 24
STATUS OF SHOOTING
|  |  |  | 1ST UNIT |  | 2ND UNIT |  | PREP | REHEARSAL |  | HOLIDAYS | TRAVEL | IDLE |  | TOTAL | X | ON SCHEDULE |  |  |  |  | DATE STARTED: |  |  |  | 2024-01-10
# OF ACTUAL DAYS |  |  |  | 1 |  | 0 |  | 0 | 3 |  | 0 | 0 | 0 |  | 1 | - | AHEAD |  | - | DAYS |  | SCHEDULED FINISH: |  |  |  | 2024-11-05
REVISED FINISH:
# OF SCHEDULED DAYS |  |  |  | 24 |  | 0 |  | 0 | 3 |  | 0 | 0 | 0 |  | 14 | - | BEHIND |  | - | DAYS |  | CURRENT SCRIPT: |  |  |  | BLUE 10/6
[22 empty] | CURRENT SCHEDULE: |  |  |  | WHITE
SCENES |  |  | SET DESCRIPTION | [13 empty] | PGS |  |  | LOCATION
20 |  |  | EXT. CANOPY ROAD-DRIVING | [13 empty] | 0.875 |  |  | LAKE HOUSE: | [5 empty] | CREW CALL |  |  | 6:00
|  |  | A luxury car whips down the canopy road. Roadkill. | [16 empty] | 2311 Two Pond Ln.
[20 empty] | Tallahassee, FL 323127 | [5 empty] | SHOOTING CALL |  |  | 7:30
27 |  |  | EXT. COURTYARD | [13 empty] | 0.125 | [8 empty] | FIRST SHOT |  |  | 7:24
|  |  | The girls roam the terrace. Lexi and Tessa take a selfie. | [22 empty] | MEAL OUT |  |  | 12:00
[26 empty] | MEAL IN |  |  | 13:00
24 |  |  | EXT. LAKE HOUSE - POOL | [13 empty] | 0.25 | [8 empty] | FIRST SHOT AFTER |  |  | 14:34
|  |  | The girls tour the pool. | [22 empty] | CAMERA WRAP |  |  | 18:14
[26 empty] | LAST MAN OUT |  |  | 19:00
44 |  |  | EXT. LAKE HOUSE - POOL | [13 empty] | 1.25 | [8 empty] | GRACE (Y/N) |  |  | N
|  |  | Ember walks out with drinks; the girls ask her to get their stuff. | [22 empty] | EXTENSION (Y/N) |  |  | N
[26 empty] | COMPANY WRAP |  |  | 19:00
31 |  |  | EXT. SIDE OF HOUSE | [13 empty] | 1.125
Ember walkd towards the woods to call Paul. She hears something.
[15 empty] | Total: |  | 3.625
SCRIPT NOTES
[5 empty] | PAGES |  |  | SCENES |  |  |  | TIME |  | SET-UPS | [7 empty] | SCENE BREAKDOWN
ORIGINAL SCRIPT |  |  |  |  | 91 |  |  | 95 |  | PREVIOUS |  | 0:00 |  | 0 |  | COMPLETED | [5 empty] | 20, 27, 24, 44, 31
REVISIONS ADDED |  |  |  |  | 1.125 |  |  | 1 | [7 empty] | PARTIALLY SHOT | [5 empty] | 21
REVISIONS DELETED |  |  |  |  | 0.5 |  |  | 1 |  | TODAY |  | 0:04 |  | 17 |  | SCHEDULED & NOT SHOT
CURRENT SCRIPT |  |  |  |  | 91.625 |  |  | 95 | [7 empty] | NOT SCHEDULED & SHOT
SHOT PREVIOUS |  |  |  |  | 0 |  |  | 0 |  | TOTAL |  | 0:04 |  | 17 |  | WILDLINES
SHOT TODAY |  |  |  |  | 3.625 |  |  | 2.5 | [7 empty] | RESHOT
TOTAL TO DATE |  |  |  |  | 3.625 |  |  | 2.5 |  | SCRIPT NOTES
TO BE SHOT |  |  |  |  | 88 |  |  | 92.5
ROLLS |  |  |  |  | SOUND |  |  |  |  | ROLLS |  | A | B
PREVIOUS |  |  |  |  | 0 |  |  | 0 |  | PREVIOUS |  | 0 | 0
TODAY |  |  |  |  | 1 |  |  | 0 |  | TODAY |  | 1 | 1
TO DATE |  |  |  |  | 0 |  |  | 0 |  | TO DATE |  | 1 | 0
EXHIBIT G
EXHIBIT G | [10 empty] | STATUS | RPT TO BASE | RPT ON SET |  | OUT FROM SET | OUT FROM BASE |  |  |  | MEAL OUT | MEAL IN | LV REST AREA | ARRV TO BASE |  | LV FROM BASE | ARRV REST AREA | MPV | STUNT ADJ |  | ADD'L NOTES
# | ACTOR | [5 empty] | ROLE
1 | Aleigha Burt | [5 empty] | EMBER |  |  |  | SW | 6:00 | 7:30 |  | 18:13 | 18:13 |  | - |  | 12:00 | 13:00 | - | - |  | - | - | - | - |  | -
2 | Jasmine Nguyen | [5 empty] | TESSA |  |  |  | SW | 6:00 | 7:30 |  | 18:28 | 16:33 |  | - |  | 12:00 | 13:00 | - | - |  | - | - | - | - |  | -
3 | Tabitha Getsy | [5 empty] | ABIGAIL |  |  |  | SW | 6:00 | 7:30 |  | 17:06 | 17:10 |  | - |  | 12:00 | 13:00 | - | - |  | - | - | - | - |  | -
4 | Jessie Roddy | [5 empty] | LEXI |  |  |  | SW | 6:00 | 7:30 |  | 14:56 | 14:56 |  | - |  | 12:00 | 13:00 | - | - |  | - | - | - | - |  | -
8 | Mark Rolston | [5 empty] | LT. DON THORNE |  |  |  | SW | 7:15 | 8:30 |  |  |  |  | - |  | 12:00 | 13:00 | - | - |  | - | - | - | - |  | -
12 | Joe Adler | [5 empty] | JEFFREY HERSTADT |  |  |  | SWF | 14:00 | 14:30 |  | 17:20 | 17:20 |  | - |  | - | - | - | - |  | - | - | - | - |  | -
13 | Hugo Armstrong | [5 empty] | DETECTIVE GUSTAFSON |  |  |  | H | H | O |  | L | L |  | - |  | - | - | - | - |  | - | - | - | - |  | -
14 | Danielle Larracuente | [5 empty] | OFFICER PAULINE CALDERON |  |  |  | W | 5:00 | 7:00 |  | 9:57 | 9:57 |  | - |  | - | - | - | - |  | - | - | - | - |  | -
18 | Janell Haney | [5 empty] | Maddie Stunt Dbl |  |  |  | H | H | O |  | L | L |  | - |  | - | - | - | - |  | - | - | - | - |  | -
32 | Michelle Jubilee Gonzalez | [5 empty] | Vasquez Stunt Dbl |  |  |  | H | H | O |  | L | L |  | - |  | - | - | - | - |  | - | - | - | - |  | -
52 | Greg Fitzpatrick | [5 empty] | Man (Harvard) |  |  |  | W | 10:30 | 11:45 |  | 16:38 | 16:38 |  | - |  | 12:00 | 13:00 | - | - |  | - | - | - | - |  | -
96 | Callie Kerns | [5 empty] | Woman (Harvard) |  |  |  | H | H | O |  | L | L |  | - |  | - | - | - | - |  | - | - | - | - |  | -
NOTES:
STATUS KEY: |  | S: Start TR: Travel W: Work H: Hold F: Finish FT: Fitting R: Rehearsal T: Test D: Drop P: Pickup | [15 empty] | NOTES KEY: |  | SA: Stunt Adjustment FC: Forced Call NDB: Non-Deductible Breakfast NP: Not Photographed K: Minor G: Grace
BACKGROUND PERFORMERS
NON-UNION
# |  | RATE |  | IN |  | MEAL |  |  | WRAP |  | NDB | MPV | ADJUSTMENTS
4 |  | -
NOTES | [25 empty] | Stand-Ins |  |  |  | 0
[26 empty] | Photo Double | Photo Double |  |  | -
[26 empty] | Non-Union BG | Non-Union BG |  |  | -
[26 empty] | TOTAL BG | TOTAL BG
SAG Mileage RT: 0 ADJUSTMENTS KEY: A: Auto C: Costume H: Hair MU: Make-Up S: Smoke W: Wet OCD: Off-Camera Dialogue P: Prop K: Minor
Unit Production Manager: | [23 empty] | 1st Assistant Director: |  |  |  | Maya Brown
[24 empty] | Key 2nd Assistant Director: |  |  |  | Hailey Odom
[8 empty] | Emma Francis | [15 empty] | 2nd 2nd Assistant Director: |  |  |  | Hailey Odom

## SAMPLE-PR Back
| CREW CALL: | 6:00 | [15 empty] | [DATE]
| GRACE (YES/NO): | N | [15 empty] | Day: _ of _
# |  |  | IN | LUNCH IN | LUNCH OUT | OUT | NDB | MPV | # |  |  | IN | LUNCH IN | LUNCH OUT | OUT | NDB | MPV | # |  |  | IN | LUNCH IN | LUNCH OUT | OUT | NDB | MPV
PRODUCTION | [8 empty] | ART DEPARTMENT | [8 empty] | PRODUCTION OFFICE
1 | Producer | Lisette Delgado | 170:24 | 12:00 | 13:00 | 439:12 |  |  | 1 | Production Designer | Ezekiel Joiner | 6:00 | 12:00 | 13:00 | 18:13 |  |  | 1 | Production Coordinator | Nyala Thomas | 5:55 | 12:00 | 13:00 | 19:00
1 | Director | Raven Carter | 170:24 | 12:00 | 13:00 | 439:12
1 | UPM | Emma Francis | 5:30 | 12:00 | 13:00 | 19:10
1 | 1st AD | Maya Brown | 6:00 | 12:00 | 13:00 | 18:13 |  |  | 1 | Art Dept Assistant | Zi Wang | 6:00 | 12:00 | 13:00 | 18:13
1 | 2nd AD | Hailey Odom | 6:00 | 12:00 | 13:00 | 19:00
1 | AD PA | Ruben Chavez | 13:00 | - | - - | 18:53
COSTUMES
[9 empty] | 1 | Set Costumer | Diego Rocha | 6:00 | 12:00 | 13:00 | 18:13
EPK
[18 empty] | 1 | EPK | Evan Patrick Adams | 5:50 | 12:00 | 13:00 | 18:20
SCRIPT SUPERVISOR
1 | Script Supervisor | Ashayla Blakely | 5:55 | 12:00 | 13:00 | 18:27 |  |  | 1 | Extras Trailer Costumer
CAMERA | [8 empty] | 1 | Costumer
1 | Director of Photography | Christopher Lee Fatt | 5:23 | 12:00 | 13:00 | 18:51 |  |  | 1 | Costumer | [7 empty] | 1 | 1.25
1 | Camera Operator | Hongqi Yao | 5:30 | 12:00 | 13:00 | 18:44 |  |  | 1 | Stitcher | [7 empty] | VFX
1 | 1st AC | Aravind Anand | 6:00 | 12:00 | 13:00 | 18:51
1 | 2nd AC | Lukas Anderson | 5:45 | 12:00 | 13:00 | 18:51
SET DECORATION
[9 empty] | 1 | Production Designer | Jonathan Horton | 6:00 | 12:00 | 13:00 | 18:13
EDITORIAL
[18 empty] | 1 | Editor | Gege He | O/C | - | - | O/C
[18 empty] | 1 | Assistant Editor | Alana Nelson | O/C | - | - | O/C
SOUND & VIDEO
1 | Sound Mixer | Miranda Colley | 5:35 | 12:00 | 13:00 | 18:40
1 | Boom Operator | Amanda Ferrari | 6:00 | 12:00 | 13:00 | 18:40
CASTING
| Sound Utility (Cast) | [16 empty] | 1 | Casting Director | Eliana Henrich | O/C | - | - | O/C
CONSTRUCTION
[18 empty] | 1 | Extras Casting Dir
SET LIGHTING
1 | Gaffer | Yiming Pan | 5:45 | 12:00 | 13:00 | 18:55
1 | BB Electric | Ghulam Quddus | 6:00 | 12:00 | 13:00 | 18:50 | [11 empty] | TRANSPORTATION
CRAFT SERVICE
OTHER CREW
| Add'l Set Lighting Technician | [7 empty] | 1 | Assist Craft Service
1 | Add'l Set Lighting Technician | [7 empty] | TECH ADVIDORS
1 | Add'l Set Lighting Technician
CATERING
GRIP
1 | Key Grip | Justin Tamayo | 6:00 | 12:00 | 13:00 | 18:51
1 | BB Grip | Alexus Spruill | 6:00 | 12:00 | 13:00 | 18:51
1 | Grip | Chris Ahrendt | 6:00 | 12:00 | 13:00 | 18:51
[11 empty] | Crew Lunches ready @ | 12:00
[11 empty] | Extras Lunches ready @ | NA
[11 empty] | Total Lunches ordered | 45
[11 empty] | Total Lunches served | 39
PROPS
1 | Prop Master | Queenie Zhang | 6:00 | 12:00 | 13:00 | 18:13
[9 empty] | 1 | Covid PA
LOCATIONS
1 | Location Mgr | Steven Hedrick Jr. | 5:45 | 12:00 | 13:00 | 19:00 |  |  | SET MEDICS | [8 empty] | PICTURE CARS
1 | Location Assistant | Tyler Kirkpatrick | 5:30 | 12:00 | 13:00 | 19:00 | [11 empty] | 1 | Bosch Jeep
[18 empty] | 1 | Black SUV
[18 empty] | 1 | Money Chandler's Car
[9 empty] | 1 | Prepping Medic
SPFX
1 | SPFX
1 | SPFX
PRODUCTION NOTES:
1 | SAFETY MEETING:
2 | MEALS:
3 | SAG MILEAGE:
4 | RE-RATES:
5 | LOSS / DAMAGE:
6 | INJURY/MEDICAL:
7 | EQUIPMENT:
8 | DGA: | MEAL ALLOWANCE:
WRAP ALLOWANCE:
EXTENDED DAY:
9 | Note | The company shot Epsiode 4 from crew call to 8:23A and from 9:50A to wrap; Epsiode 2 from 823A to 950A .
The Company moved from location 1 (Red Studios) to location 2 (800 S Plymouth Blvd, 90005) at 437P.